## Sheet1
PROJECT X - Automated Attendance System
Task ID | Task Name | Sub Task ID | Sub Task Name | Deliverables | Estimated Hours | Assignee | Start Date | End Date | Status | Actual Hours Spent | Notes
1 | Initiation Phase | 1.1 | Define project objectives | Project scope document | 4 | Sophie Bohol | 02/27/2025 | 02/27/2025 | Done | 3
|  | 1.2 | Identify Stakeholders | Stakeholder list | 6 | Sophie Bohol | 02/28/2025 | 2025-01-03 | Done | 4
|  | 1.3 | Perform Feasibility Analysis | Feasibility report | 5 | Sophie Bohol | 2025-01-03 | 2025-02-03 | Done | 5
|  | 1.4 | Outline Project Timeline | Project plan document | 6 | Jhomarie Avenido | 2025-01-03 | 2025-02-03 | Done | 6
|  | 1.5 | Obtain approvals | Approved project charter | 5 | Sophie Bohol | 2025-01-03 | 2025-02-03 | Done | 5
2 | System Analysis | 2.1 | Gather functional requirements | Requirement specification document | 5 | Sophie Bohol | 2025-02-03 | 2025-01-08 | Done | 5
|  | 2.2 | Gather non-functional requirements | Performance & security requirements | 7 | Sophie Bohol | 2025-02-03 | 2025-01-09 | Done | 4
|  | 2.3 | Define system architecture | System architecture diagram | 8 | Sophie Bohol | 2025-03-03 | 2025-01-10 | Done | 5
|  | 2.4 | Create wireframes/mockups | UI wireframes | 10 | Cloe Mabanding | 2025-03-03 | 2025-01-11 | Done | 5
3 | System Design | 3.1 | Database design | ERD and database schema | 5 | Cloe Mabanding | 2025-05-03 | 2025-06-03 | Done | 6
|  | 3.2 | API design | API documentation | 5 | Jhomarie Avenido | 2025-05-03 | 2025-06-03 | Done | 6
|  | 3.3 | UI/UX design | Final UI/UX designs | 7 | Maureen Portillo | 2025-06-03 | 2025-07-03 | Done | 6
|  | 3.4 | Security design | Security measures document | 10 | Maureen Portillo | 2025-10-03 | 2025-11-03 | Done | 5
4 | Implementation Phase | 4.1 | Set up development environment | Configured development tools | 6 | Cloe Mabanding | 03/15/2025 | 03/16/2025 | Done | 5
|  | 4.2 | Frontend development (React Native) | Initial UI screens | 6 | Cloe Mabanding | 03/16/2025 | 03/17/2025 | Done | 6
|  | 4.3 | Backend development | Working backend APIs | 7 | Cloe Mabanding | 03/16/2025 | 03/17/2025 | Done | 5
|  | 4.4 | QR Code scanning implementation | Functional QR scanner module | 8 | Cloe Mabanding | 03/18/2025 | 03/19/2025 | Done | 5
|  | 4.5 | Testing unit integration | Test reports | 8 | Maureen Portillo | 03/20/2025 | 03/21/2025 | Done | 6
5 | Quality Assurance Phase | 5.1 | Functional testing | Test case reports | 9 | Maureen Portillo | 03/28/2025 | 03/29/2025 | Done | 6
|  | 5.2 | Security testing | Security vulnerability report | 10 | Maureen Portillo | 2025-03-04 | 2025-04-04 | Done | 8
|  | 5.3 | User acceptance testing | User feedback & approval | 8 | Maureen Portillo | 2025-04-04 | 2025-05-04 | Done | 9
6 | Deployment | 6.1 | Prepare deployment environment | Deployment guide | 8 | Cloe Mabanding | 2025-06-04 | 2025-07-04 | Done | 9
|  | 6.2 | Deploy backend API | Hosted backend | 9 | Cloe Mabanding | 2025-08-04 | 2025-09-04 | Done | 10
|  | 6.3 | Deploy mobile app (beta) | Beta version released | 9 | Cloe Mabanding | 2025-09-04 | 2025-10-04 | Done | 10
|  | 6.4 | Fix deployment issues | Issue resolution report | 8 | Cloe Mabanding | 2025-10-04 | 2025-11-04 | Done | 9
|  | 6.5 | Release final version | Live mobile app | 10 | Cloe Mabanding | 2025-12-04 | 04/13/2025 | Done | 11
7 | Final Demonstration | 7.1 | Prepare presentation materials | Prepare presentation materials | 11 | Cloe Mabanding | 04/14/2025 | 04/15/2025 | Done | 10
|  | 7.2 | Conduct demo for stakeholders | Live demonstration | 6 | Cloe Mabanding | 04/16/2025 | 04/17/2025 | Done | 8
|  | 7.3 | Gather final feedback | Feedback report | 7 | Sophie Bohol | 04/18/2025 | 04/19/2025 | Done | 9
|  | 7.4 | Project closure & documentation | Final project report | 8 | Cloe Mabanding | 04/20/2025 | 04/21/2025 | Done | 9